## Sheet1
Performance or Feature Issue | Bug? | Fix
Uniform Background/Font | N | Create a style for each activity to reference
Button Image Scaling- Main Activity | N
Button Image Scaling- Selection Activity | N
Create custom logo for App | N | Photoshop a new image
Add extra pages to stock activity for more pictures | N | low priority
Save photo to correct place (gallery) frpm camera | N
Camera image is rotate 90 degrees in PhotoEdit | Y
Incomplete Features |  | Status
Add text to image |  | complete
Save camera image |  | complete
Load camera image to be edited |  | complete
save edited image |  | in progress
delete text off edited image |  | complete
post edited image to twitter |  | in progress
post edited image to facebook |  | not yet begun
Update UI |  | in progress