## Sheet1
Bug ID | Bug Description | Possible Fix
1 | Saving Camera Image- Image is saved rotated 90 degrees | No clear idea, perhaps rotate image before it is saved. Make sure the image passed to Photo Edit is then unrotated, as it rotates
2 | Rotating Camera- aspect ratio changes, image is stretched/sqiushed | Camera Intent might be opening a square image, not one proportional to the widescreen aspect ratio of a tablet
3 | Cannot sign out of twitter through app | Not implemented- add feature
4 | Front facing camera is shown flipped in photo edit | Might be a feature of device's camera, could be an effect of having front-facing camera. Test on another device, and perhaps flip image if users complain
5 | "Select a different photo" says instameme has encountered error | Sends you to selection activity, so not a big problem. Is probably trying to open the selection intent outside of the activity that it is called in. Look in to that
6 | Text alpha is lowered if you hit "back" button on posting activity | When image is saved, alpha of background is set to 0, then entire edit text is set to .5. Make just the background alpha change.
7 | Instameme has encoutnered error when hitting back and returning to camera | Trying to load camera intent outside of camera activity, change what it calls